## Sheet1
Test Case ID | Description | Steps | Expected Result | Actual Result | Status | Severity | Assigned To | Remarks
2 | TC001 | Verify product listing displays correctly | Open marketplace, check product listings | All products displayed accurately | Products displayed as expected | Passed | Low | - | Test successful
3 | TC002 | Test search functionality | Search for a specific product | Relevant products displayed | Search results match query, but slight error in results | Failed | Medium | - | Search function not fully accurate, requires improvement
4 | TC003 | Validate cart operations | Add, update, and remove items from cart | Cart updates correctly | Cart operations functioning | Passed | High | - | Cart operations working well
5 | TC004 | Check dynamic routing for product pages | Click on product to open detailed page | Product detail pages load correctly | Pages load without errors | Passed | Low | - | No issues found
6 | TC005 | Test error handling for API failures | Simulate API failure and check error handling | Error message displayed properly | Error messages displayed, fallback UI is shown | Passed | High | - | Implemented fallback UI successfully
7 | TC006 | Performance optimization for load time | Measure page load time | Page load time under 3 seconds | Page load time measured at 3.2 seconds | Failed | Medium | - | Performance improvement needed
8 | TC007 | Cross-browser testing on Chrome and Firefox | Test on Chrome, Firefox | Consistent rendering and functionality | Rendering consistent across both browsers | Passed | Medium | - | No issues found
9 | TC008 | Device testing on physical mobile device | Test on mobile device | Correct display and functionality on mobile | Functionality working as expected | Passed | Medium | - | Responsive design verified
10 | TC009 | API communication over HTTPS | Verify API communication is secure | API calls made over HTTPS | API calls are over HTTP instead of HTTPS | Failed | Critical | - | API communication needs to be secured
11 | TC010 | Simulate user interactions for UAT | Simulate browsing, adding items to cart, checkout | All workflows are intuitive and error-free | All workflows function smoothly without errors | Passed | Low | - | UAT completed successfully
12 | TC011 | Update documentation for testing results | Ensure all test cases, results, and fixes are documented | All steps and results clearly documented | Documentation is complete and well-structured | Passed | Low | - | Documentation updated successfully